## HOT END
Hot End Long-term Work Plan
Legend
FREQ | - 1W/3D means a 1 week schedule with 3 daily tasks during that week |  |  |  |  | 1 W/D means a 1 week schedule with daily tasks
MWF | - Monday, Wednesday, Friday
No. of people | - Means the number of tradespeople from one Work Centre that will perform the schedule
Man HRS | - Means the accumulative work hours, of all tradespeople from one Work Centre, that will perform the schedule
DUR | - Means the total downtime of the equipment | [9 empty] | Total hours per week: |  |  |  |  | 115 | 109.5 | 122.5 | 182.5 | 107.5 | 109.5 | 108.5 | 194 | 107.5 | 115 | 108.5 | 254.5 | 113.5 | 113.5 | 119.5 | 255.5 | 125.5 | 112.5 | 108.5 | 180 | 126.5 | 116 | 108.5 | 187 | 131 | 109.5 | 122.5 | 178.5 | 107.5 | 109.5 | 108.5 | 195 | 107.5 | 115 | 105.5 | 188 | 113.5 | 160 | 122.5 | 197.5 | 107.5 | 174.5 | 108.5 | 180 | 110.5 | 118 | 124.5 | 185 | 113.5 | 109.5 | 137 | 178.5
FunctLocation | Equipment | Equipment descript. | MnWkCtr | MntPlan | Type | Group | GrC | Maint Item | Description |  | FREQ | No of People | Man HRS | DUR |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
HOT END
PFG-F1-HOE |  |  | FL1CONT | F1-POS-1 | A | COMB-POS | 1 | 5501 | SERVICE CANAL & COMBUS AIR POS. 1&2 LHS |  | 24 W | 1 | 3 | 3 |  | W23: 3; W47: 3
BATH
PFG-F1-HOE-BTH |  |  | FL1MECH | F1-HOE-WKS | A | BATHPLUM | 1 | 2822 | Inspection - Bath service mains(Plumber) |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CANAL
PFG-F1-HOE-BTH-CAN | 10000981 | CANAL TEMPERATURE CONTROL | FL1CONT | F1-HOE-WKS | A | F1CT | 1 | 423 | Service on canal temperature inst. |  | 26 W | 1 | 3 | 3 |  | W12: 3; W38: 3
PFG-F1-HOE-BTH-CAN | 10000882 | OPERATIONAL TWEEL | FL1ELEC | F1-HOE-WKS | E | 25 | 1 | 482 | Visual on tweel and raising gear |  | 8 W | 1 | 1 | 1 | bar: W8; W16; W24; W32; W40; W48
NARROW SECTION
PFG-F1-HOE-BTH-NAR | 10001120 | N2 SPILL CONTROL INSTRUMENTATION | FL1CONT |  |  |  |  | 434 | Service on N2 spill control inst |  | 26 W | 1 | 3 | 3 | * | W16: 3; W42: 3
PFG-F1-HOE-BTH-NAR | 10000907 | LIFT OUT ROLLERS AND DRIVE | FL1MECH | F1-HOE-WKS | E | 28 | 1 | 451 | Service on lift out rollers drive |  | 1 W | 1 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PFG-F1-HOE-BTH-NAR | 10000910 | SO2 SYSTEM | FL1MECH | F1-HOE-WKS | E | 29 | 1 | 497 | SO2 storage system service |  | 2 W | 1 | 2 | 2 |  | W2: 2; W4: 0; W6: 2; W8: 0; W10: 2; W12: 0; W14: 2; W16: 0; W18: 2; W20: 0; W22: 2; W24: 0; W26: 2; W28: 0; W30: 2; W32: 0; W34: 2; W36: 0; W38: 2; W40: 0; W42: 2; W44: 0; W46: 2; W48: 0; W50: 2; W52: 0
PFG-F1-HOE-BTH-NAR | 10000910 | SO2 SYSTEM | FL1MECH | F1-HOE-WKS | E | 29 | 1 | 497 | SO2 STORAGE SCHEDULE Monthly |  | 4 W | 1 | 5 | 5 |  | W4: 5; W8: 5; W12: 5; W16: 5; W20: 5; W24: 5; W28: 5; W32: 5; W36: 5; W40: 5; W44: 5; W48: 5; W52: 5
TEMPERATURE
PFG-F1-HOE-BTH-TEM | 10000957 | EDGE FOLLOWING BURNERS (B-Zone burners) | FL1CONT | [5 empty] | B-Zone Burners service & calibrate |  | 12 W | 1 | 4 | 4 | * | W1: 4; W13: 4; W25: 4; W37: 4; W49: 4
PFG-F1-HOE-BTH-TEM | 10000921 | TEMPORARY BURNERS | FL1CONT | [5 empty] | T - Burners service |  | 12 W | 1 | 2 | 2 | * | W1: 2; W13: 2; W25: 2; W37: 2; W49: 2
BATHROOF HEATING TRANSFORMERS (1-29)
PFG-F1-HOE-BTH-TEM-TRA | 10001026 | B/ROOF HEATING TRANSFORMER 1 | FL1ELEC | F1-HOE-WKS | E | 49 | 1 | 478 | Service on transformers |  | 8 W | 1 | 3 | 3 |  | W8: 3; W16: 3; W24: 3; W32: 3; W40: 3; W48: 3
WIDE SECTION
PFG-F1-HOE-BTH-WID |  |  | FL1CONT | F1-HOE-WKS | A | CSTR | 1 | 392 | Calibration on top roll machines |  | 4 W | 1 | 2 | 2 |  | W4: 2; W8: 2; W12: 2; W16: 2; W20: 2; W24: 2; W28: 2; W32: 2; W36: 2; W40: 2; W44: 2; W48: 2; W52: 2
PFG-F1-HOE-BTH-WID | 10000902 | TOP ROLLERS ELECTRICAL DRIVE & CONTROL | FL1ELEC | F1-HOE-WKS | E | 26 | 1 | 382 | Visual Alternator set on top roll drive |  | 12 W | 1 | 1 | 1 | bar: W4; W16; W28; W40; W52
PFG-F1-HOE-BTH-WID | 10000906 | PERISCOPES | FL1ELEC | F1-HOE-WKS | E | 27 | 1 | 488 | Service on periscope cooling water pumps |  | 13 W | 1 | 1 | 1 | bar: W12; W25; W38; W51
PFG-F1-HOE-BTH-WID |  |  | FL1ELEC | F1-HOE-WKS | A | TOPE | 1 | 480 | Visual Minor top roller service |  | 4 W | 1 | 2 | 2 |  | W4: 2; W8: 2; W12: 2; W16: 2; W20: 2; W24: 2; W28: 2; W32: 2; W36: 2; W40: 2; W44: 2; W48: 2; W52: 2
PFG-F1-HOE-BTH-WID |  |  | FL1MECH | F1-HOE-WKS | A | TOPM | 1 | 479 | Minor top roller service Mech |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
AIRCONS
PFG-F1-HOE-BUI-AIR | 10001106 | VENT FANS | FL1ELEC | F1-HOE-WKS | E | 54 | 1 | 409 | Fan filter service on vent fans |  | 12 W | 1 | 3 | 3 |  | W3: 3; W15: 3; W27: 3; W39: 3; W51: 3
PFG-F1-HOE-BUI-AIR | 10001542 | CHILLED WATER HANDLER | FL1ELEC | F1-HOE-WKS | E | 78 | 1 | 395 | Service on chilled water handler |  | 18 W | 1 | 1 | 1 | bar: W4; W22; W40
PFG-F1-HOE-BUI-AIR | 10001542 | CHILLED WATER HANDLER | FL1ELEC | F1-HOE-WKS | E | 78 | 2 | 396 | Filters on chilled water handler |  | 4 W | 1 | 0.5 | 0.5 |  | W4: 0.5; W8: 0.5; W12: 0.5; W16: 0.5; W20: 0.5; W24: 0.5; W28: 0.5; W32: 0.5; W36: 0.5; W40: 0.5; W44: 0.5; W48: 0.5; W52: 0.5
PFG-F1-HOE-BUI-AIR | 10001084 | HEATING, VENTILATION & AIRCONDITIONING | FL1ELEC | F1-HOE-WKS | A | F1AF | 1 | 495 | Aircon filters Hot End (D)(1) |  | 4 W | 1 | 1 | 1 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
BUILDINGS
PFG-F1-HOE-BUI-BLD | 10001094 | BATH BUILDINGS | FL1CONT | F1-HOE-WKS | A | 102 | 1 | 4761 | CHECK SPARE MONITORS AT BATH & STORE |  | 1 W | 1 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LOCAL ELECTRICS
PFG-F1-HOE-BUI-LOC |  |  | FL1ELEC | F1-HOE-WKS | T | 3 | 1 | 401 | Service on DB's |  | 26 W | 1 | 16 | 16 |  | W12: 16; W38: 16
SERVICE MAINS
PFG-F1-HOE-BUI-SER |  |  | FL1CONT | F1-HOE-WKS | T | 6 | 4 | 426 | Service compressed air inst. |  | 26 W | 1 | 4 | 4 |  | W14: 4; W40: 4
PFG-F1-HOE-BUI-SER |  |  | FL1CONT | F1-HOE-WKS | T | 6 | 2 | 487 | Service on water system lehr |  | 4 W | 1 | 4 | 4 |  | W4: 4; W8: 4; W12: 4; W16: 4; W20: 4; W24: 4; W28: 4; W32: 4; W36: 4; W40: 4; W44: 4; W48: 4; W52: 4
PFG-F1-HOE-BUI-SER |  |  | FL1MECH | F1-HOE-WKS | T | 6 | 1 | 486 | Service on water system furnace |  | 1W/5D | 1 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
BATH
PFG-F1-HOE-CON-BTH | 10001105 | BATH COOLING INSTRUMENTATION | FL1CONT | F1-HOE-WKS | E | 53 | 1 | 422 | Bath recirculating water inst. service |  | 13 W | 1 | 2 | 2 |  | W12: 2; W25: 2; W38: 2; W51: 2
PFG-F1-HOE-CON-BTH | 10000992 | BATH RECORDERS | FL1CONT | F1-HOE-WKS | E | 40 | 1 | 463 | Service on bath recorders |  | 1W/5D | 1 | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
PFG-F1-HOE-CON-BTH | 10001105 | BATH COOLING INSTRUMENTATION | FL1CONT | F1-HOE-WKS | E | 53 | 2 | 441 | Service on water cooling inst. |  | 26 W | 1 | 2 | 2 |  | W12: 2; W38: 2
PFG-F1-HOE-CON-BTH | 10000985 | PRESSURE CONTROL | FL1CONT | F1-HOE-WKS | E | 36 | 1 | 421 | Service bath pressure inst. |  | 26 W | 1 | 4 | 4 |  | W12: 4; W38: 4
PFG-F1-HOE-CON-BTH | 10001121 | SO2 SYSTEM INSTRUMENTATION | FL1CONT | F1-HOE-WKS | E | 62 | 2 | 439 | Minor service on SO2 system inst. |  | 4 W | 1 | 3 | 3 |  | W4: 3; W8: 3; W12: 0; W16: 3; W20: 3; W24: 3; W28: 3; W32: 3; W36: 0; W40: 3; W44: 3; W48: 3; W52: 3
PFG-F1-HOE-CON-BTH | 10001121 | SO2 SYSTEM INSTRUMENTATION | FL1CONT | F1-HOE-WKS | E | 62 | 1 | 438 | Major service on SO2 system inst. |  | 24 W | 1 | 8 | 8 |  | W12: 8; W36: 8
PFG-F1-HOE-CON-BTH | 10001025 | GAS PRESSURE CONTROL & INST. BATH | FL1CONT |  |  |  |  | 391 | Calibration on bath pressure inst |  | 26 W | 1 | 2 | 2 | * | W12: 2; W38: 2
BATH CALIBRATION
PFG-F1-HOE-CON-BTH-CAL | 10000989 | SUBSTANCE GAUGE (BATH) HOT END | FL1CONT | F1-HOE-WKS | E | 39 | 1 | 440 | Service on substance gauge |  | 12 W | 1 | 4 | 4 |  | W10: 4; W22: 4; W34: 4; W46: 4
FURNACE
PFG-F1-HOE-CON-FUR | 10005015 | FURNACE REVERSAL SYSTEM | FL1CONT | F1-UPS | A | SP3-UPS | 2 | 5397 | 2 YEARLY UPS BATTERY CHANGE FURNACE REVE |  | 104 W | 1 | 1.5 | 1.5
PFG-F1-HOE-CON-FUR | 10000956 | METAL LEVEL CONTROLLER & INST | FL1CONT | F1-HOE-WKS | E | 31 | 1 | 432 | Service on metal level instrumentation |  | 12 W | 1 | 3 | 3 |  | W7: 3; W19: 3; W31: 3; W43: 3
PFG-F1-HOE-CON-FUR | 10001128 | REVERSAL SYSTEM PANELS | FL1CONT | F1-HOE-WKS | E | 67 | 1 | 453 | Cleaning of Furnace Reversal panels |  | 13 W | 1 | 3 | 3 |  | W12: 3; W25: 3; W38: 3; W51: 3
PFG-F1-HOE-CON-FUR | 10001115 | FURNACE RECORDERS | FL1CONT | F1-HOE-WKS | E | 60 | 2 | 464 | Serv. on furn. record. conf.weekly |  | 1W/5D | 1 | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
PFG-F1-HOE-CON-FUR | 10001019 | Z & J PNEUMATICS | FL1CONT | F1-HOE-WKS | E | 47 | 1 | 450 | Pneumatic limit switches on Z&J |  | 2 W | 1 | 1 | 1 | bar: W1; W3; W5; W7; W9; W11; W13; W15; W17; W19; W21; W23; W25; W27; W29; W31; W33; W35; W37; W39; W41; W43; W45; W47; W49; W51
PFG-F1-HOE-CON-FUR | 10005125 | COMBUSTION AIR INST 1 & 2 RHS | FL1CONT | F1-POS-2 | A | COMB-POS | 1 | 5502 | SERVICE COMBUSTION AIR POS. 1&2 RHS |  | 24 W | 1 | 3 | 3 |  | W3: 3; W27: 3; W51: 3
PFG-F1-HOE-CON-FUR | 10000959 | BUBBLER CONTROLLER AND INSRUMENTATION | FL1CONT | F1-HOE-WKS | E | 32 | 1 | 424 | Service bubbler instrumentation |  | 24 W | 1 | 4 | 4 |  | W12: 4; W36: 4
PFG-F1-HOE-CON-FUR | 10005127 | COMBUSTION AIR INST 3 & 4 RHS | FL1CONT | F1-POS-4 | A | COMB-POS | 1 | 5504 | SERVICE COMBUSTION AIR POS. 3&4 RHS |  | 24 W | 1 | 3 | 3 |  | W12: 3; W36: 3
PFG-F1-HOE-CON-FUR | 10005128 | COMBUSTION AIR INST 5 & 6 LHS | FL1CONT | F1-POS-5 | A | COMB-POS | 1 | 5505 | SERVICE COMBUSTION AIR POS. 5&6 LHS |  | 24 W | 1 | 3 | 3 |  | W16: 3; W40: 3
PFG-F1-HOE-CON-FUR | 10005129 | COMBUSTION AIR INST 5 & 6 RHS | FL1CONT | F1-POS-6 | A | COMB-POS | 1 | 5506 | SERVICE COMBUSTION AIR POS. 5&6 RHS |  | 24 W | 1 | 3 | 3 |  | W21: 3; W45: 3
PFG-F1-HOE-CON-FUR | 10005126 | COMBUSTION AIR INST 3 & 4 LHS | FL1CONT | F1-POS-3 | A | COMB-POS | 1 | 5503 | SERVICE COMBUSTION AIR POS. 3&4 LHS |  | 24 W | 1 | 3 | 3 |  | W8: 3; W32: 3
PFG-F1-HOE-CON-FUR | 10000983 | FURNACE PRESS & DRAUGHT CONTR. & INST | FL1CONT |  |  |  |  | 427 | Service on furn press & draught inst |  | 26 W | 1 | 2 | 2 | * | W16: 2; W42: 2
PFG-F1-HOE-CON-FUR | 10001110 | FRONT WALL COOLING FANS CONTROL | FL1CONT |  |  |  |  | 429 | Service on front wall fans inst. |  | 26 W | 1 | 2 | 2 | * | W16: 2; W42: 2
PFG-F1-HOE-CON-FUR | 10001125 | GAS PRESSURE & FLOW INST. FURNACE | FL1CONT |  |  |  |  | 430 | Service on gas instrumentation |  | 26 W | 2 | 18 | 9 | * | W16: 18; W42: 18
PFG-F1-HOE-CON-FUR | 10001127 | OIL FIRING INSTRUMENTATION | FL1CONT |  |  |  |  | 435 | Service on oil firing inst. |  | 26 W | 2 | 18 | 9 | * | W16: 18; W42: 18
PFG-F1-HOE-CON-FUR | 10001546 | SPOOL VALVES | FL1CONT | F1-HOE-WKS | E | 80 | 1 | 472 | Service on spool valves |  | 26 W | 1 | 16 | 16 |  | W21: 16; W47: 16
PFG-F1-HOE-CON-FUR | 10001123 | COMBUSTION AIR CONTROL & INSTRUMENTATION | FL1CONT | F1-HOE-WKS | E | 63 | 1 | 455 | Service on valve positioners |  | 52 W | 1 | 18 | 18 |  | W17: 18
PFG-F1-HOE-CON-FUR | 10001111 | STOCK FRIT BOGIE cont | FL1ELEC | F1-HOE-WKS | E | 57 | 1 | 403 | Drive & control on stock frit bogie |  | 13 W | 1 | 1 | 1 | bar: W12; W25; W38; W51
PFG-F1-HOE-CON-FUR | 10001110 | FRONT WALL COOLING FANS CONTROL | FL1ELEC | F1-HOE-WKS | E | 56 | 1 | 404 | Front wall fans drive and control |  | 13 W | 1 | 1 | 1 | bar: W12; W25; W38; W51
PFG-F1-HOE-CON-FUR | 10001021 | FEEDER PLC | FL1ELEC | F1-COE-WKS | A | FANS | 4 | 5521 | Clean filter on Feeder MWF |  | 1W/3D | 1 | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
PFG-F1-HOE-CON-FUR | 10001124 | Z & J CONTROL | FL1ELEC | F1-HOE-WKS | E | 64 | 1 | 406 | Drive & control on Z & J valves |  | 4 W | 1 | 2 | 2 |  | W4: 2; W8: 2; W12: 2; W16: 2; W20: 2; W24: 2; W28: 2; W32: 2; W36: 2; W40: 2; W44: 2; W48: 2; W52: 2
PFG-F1-HOE-CON-FUR | 10001107 | SUPERSTRUCTURE FANS CONT & INSTRUMENT | FL1ELEC | F1-HOE-WKS | E | 55 | 1 | 405 | Drive & control on s/structure fans |  | 6 W | 1 | 1.5 | 1.5 |  | W4: 1.5; W10: 1.5; W16: 1.5; W22: 1.5; W28: 1.5; W34: 1.5; W40: 1.5; W46: 1.5; W52: 1.5
LEHR
PFG-F1-HOE-CON-LEH | 10000996 | LEHR INSTRUMENTATION AND CONTROL PANELS | FL1CONT | F1-HOE-WKS | E | 42 | 1 | 443 | Service lehr control panels |  | 16 W | 1 | 2 | 2 |  | W8: 2; W24: 2; W40: 2
PFG-F1-HOE-CON-LEH | 10001113 | LEHR RECORDERS | FL1CONT | F1-HOE-WKS | E | 59 | 1 | 462 | Serv. on lehr record. conf. weekly |  | 1W/5D | 1 | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
PFG-F1-HOE-CON-LEH | 10001112 | PYROMETER INSTRUMENTATION | FL1CONT | F1-HOE-WKS | A | PYRT | 1 | 459 | Service on pyro tank & instrumentation |  | 26 W | 1 | 2 | 2 |  | W12: 2; W38: 2
PFG-F1-HOE-CON-LEH | 10001112 | PYROMETER INSTRUMENTATION | FL1CONT |  |  |  |  | 431 | Service on pyro instrumentation |  | 26 W | 1 | 4 | 4 | * | W16: 4; W42: 4
PFG-F1-HOE-CON-LEH | 10000997 | ALARM SYSTEM (LEHR) | FL1CONT | F1-HOE-WKS | E | 43 | 1 | 419 | Service on alarm instrumentation |  | 4 W | 1 | 6 | 6 |  | W4: 6; W8: 6; W12: 6; W16: 6; W20: 6; W24: 6; W28: 6; W32: 6; W36: 6; W40: 6; W44: 6; W48: 6; W52: 6
FURNACE
PFG-F1-HOE-FUR |  |  | FL1ELEC | F1-HOE-WKS | A | FIBU | 1 | 491 | Filters work end and refinery burnersMWF |  | 1W/3D | 1 | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
PFG-F1-HOE-FUR |  |  | FL1MECH | F1-HOE-WKS | A | F1SU | 1 | 397 | Cleaning on s/structure & front wall |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
FEEDER
PFG-F1-HOE-FUR-FEE |  |  | FL1ELEC | F1-HOE-WKS | A | 211 | 1 | 5384 | Service Feeder Electrical |  | 2 W | 1 | 1 | 1 | bar: W2; W4; W6; W8; W10; W12; W14; W16; W18; W20; W22; W24; W26; W28; W30; W32; W34; W36; W38; W40; W42; W44; W46; W48; W50; W52
PFG-F1-HOE-FUR-FEE |  |  | FL1MECH | F1-HOE-WKS | T | 7 | 2 | 407 | Service on feeder |  | 1 W | 1 | 4.5 | 4.5 |  | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
PFG-F1-HOE-FUR-FEE |  |  | FL1MECH | F1-HOE-WKS | T | 7 | 1 | 408 | Drive change-over on feeder |  | 1 W | 1 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
PFG-F1-HOE-FUR-FEE | 10000021 | CONVEYOR FC6 (FURNACE) | FL1MECH | F1-HOE-WKS | A | CONM | 1 | 95 | Minor mechanical for FC6 |  | 1W/5D | 1 | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
PFG-F1-HOE-FUR-FEE | 10000022 | CONVEYOR FC7 FOR SHUTTLE (ABOVE FEEDER) | FL1MECH | F1-HOE-WKS | E | 242 | 1 | 96 | Minor mechanical for FC7 |  | 1W/5D | 1 | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
PFG-F1-HOE-FUR-FEE | 10000802 | STOCK FRIT BOGIE | FL1MECH | F1-HOE-WKS | E | 16 | 1 | 469 | Service on stock frit bogie |  | 26 W | 1 | 1 | 1 | bar: W12; W38
BUNKER
PFG-F1-HOE-FUR-FEE-BUN | 10000800 | LEVEL PROBES | FL1ELEC | F1-HOE-WKS | E | 15 | 1 | 456 | Service on level probes |  | 13 W | 1 | 1.5 | 1.5 |  | W12: 1.5; W25: 1.5; W38: 1.5; W51: 1.5
SPADES
PFG-F1-HOE-FUR-FEE-SPA | 10000799 | WATER BOXES (PUSHERS) (SPADE) | FL1MECH | F1-HOE-WKS | A | FEED | 1 | 2821 | Inspection-Feeder service mains(Plumber) |  | 1W/5D | 1 | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
WATER SYSTEM
PFG-F1-HOE-FUR-FEE-WAT | 10001116 | SUMP PUMP 1 | FL1ELEC | F1-HOE-WKS | A | SUME | 1 | 474 | Electrical sump pumps-Furnace 1-5 & Lehr |  | 8 W | 1 | 1.5 | 1.5 |  | W8: 1.5; W16: 1.5; W24: 1.5; W32: 1.5; W40: 1.5; W48: 1.5
COOLING
PFG-F1-HOE-FUR-MEL-COO | 10001002 | DIESEL BACK UP FAN FOR FRONTWALL COOLING | FL1ELEC | F1-DIESELRUN | E | 44 | 1 | 399 | Diesel test run on front wall back-up |  | 4 W | 1 | 1 | 1 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
PFG-F1-HOE-FUR-MEL-COO | 10001002 | DIESEL BACK UP FAN FOR FRONTWALL COOLING | FL1ELEC | F1-HOE-WKS | A | F1BB | 1 | 384 | Batt. maint. on diesel back-up wall fan |  | 8 W | 1 | 1 | 1 | bar: W8; W16; W24; W32; W40; W48
FUEL AND FIRING
PFG-F1-HOE-FUR-MEL-FUE |  |  | FL1CONT | F1-UPS | A | SP3-UPS | 2 | 5398 | 2 YEARLY UPS BATTERY CHANGE FURNACE BOOS |  | 104 W | 1 | 1.5 | 1.5 |  | W1: 1.5
PFG-F1-HOE-FUR-MEL-FUE |  |  | FL1CONT | F1-HOE-WKS | A | OLFR | 1 | 452 | Inspection on oil firing |  | 26 W | 1 | 6 | 6 |  | W12: 6; W38: 6
PFG-F1-HOE-FUR-MEL-FUE | 10000829 | GAS FIRING | FL1CONT |  |  |  |  | 437 | Service on gas firing inst. |  | 26 W | 2 | 18 | 9 | * | W16: 18; W42: 18
PFG-F1-HOE-FUR-MEL-FUE | 10000829 | GAS FIRING | FL1CONT | F1-HOE-WKS | E | 21 | 2 | 414 | Test for gas leaks |  | 4 W | 1 | 3 | 3 |  | W4: 3; W8: 3; W12: 3; W16: 3; W20: 3; W24: 3; W28: 3; W32: 3; W36: 3; W40: 3; W44: 3; W48: 3; W52: 3
PFG-F1-HOE-FUR-MEL-FUE | 10004093 | Wobbe Meter | FL1CONT | F1-HOE-WKS | E | 241 | 1 | 4842 | WOBBE MONTHLY MINOR INSPECTION |  | 4 W | 1 | 4 | 4 |  | W4: 4; W8: 4; W12: 4; W16: 4; W20: 4; W24: 4; W28: 4; W32: 4; W36: 4; W40: 4; W44: 4; W48: 4; W52: 4
PFG-F1-HOE-FUR-MEL-FUE | 10000832 | ATOMIZING AIR & INSTRUMENTATION | FL1CONT | F1-HOE-WKS | E | 23 | 1 | 418 | Service on atomizing air instrumentation |  | 52 W | 1 | 16 | 16 |  | W12: 16
PFG-F1-HOE-FUR-MEL-FUE | 10000821 | COMBUSTION AIR FAN & DUCTING STAGE 1 | FL1ELEC | F1-HOE-WKS | A | COME | 1 | 398 | Electrical on comb. air fan |  | 12 W | 1 | 1 | 1 | bar: W3; W15; W27; W39; W51
PFG-F1-HOE-FUR-MEL-FUE | 10000830 | ELECTRICAL BOOST | FL1ELEC | F1-HOE-WKS | E | 22 | 1 | 494 | Visual on electrical boost |  | 12 W | 1 | 2 | 2 |  | W3: 2; W15: 2; W27: 2; W39: 2; W51: 2
PFG-F1-HOE-FUR-MEL-FUE | 10000822 | DIESEL COMBUSTION AIR BACK-UP | FL1ELEC | F1-HOE-WKS | A | F1AB | 1 | 385 | Batt. maint. on diesel back-up comb fans |  | 4 W | 1 | 1 | 1 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
PFG-F1-HOE-FUR-MEL-FUE | 10000822 | DIESEL COMBUSTION AIR BACK-UP | FL1ELEC | F1-DIESELRUN | E | 19 | 1 | 400 | Diesel test run on comb. air back-up |  | 4 W | 1 | 1 | 1 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
PFG-F1-HOE-FUR-MEL-FUE | 10000831 | BUBBLERS | FL1MECH | F1-HOE-WKS | A | BUBLPLUM | 1 | 2861 | Inspection on bubbler service mains |  | 1 W | 1 | 1 | 1 | bar: W1 to W52
PFG-F1-HOE-FUR-MEL-FUE | 10000829 | GAS FIRING | FL1MECH | F1-HOE-WKS | E | 21 | 1 | 413 | Inspection on gas firing |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
PFG-F1-HOE-FUR-MEL-FUE |  |  | FL1MECH | F1-HOE-WKS | A | HEAX | 1 | 416 | Service on heat exchanger 1 |  | 8 W | 1 | 16 | 16 |  | W8: 16; W16: 16; W24: 16; W32: 16; W40: 16; W48: 16
PFG-F1-HOE-FUR-MEL-FUE | 10000825 | SIDE PORT BURNER BLOCKS | FL1MECH | F1-HOE-WKS | A | F1BU | 1 | 1115 | Service side port burner blocks |  | 8 W | 1 | 6 | 6 |  | W8: 6; W16: 6; W24: 6; W32: 6; W40: 6; W48: 6
PFG-F1-HOE-FUR-MEL-FUE |  |  | FL1MECH | F1-HOE-WKS | A | F1BU | 1 | 390 | Side port burner service on port necks |  | 8 W | 2 | 6 | 6 |  | W4: 6; W12: 6; W20: 6; W28: 6; W36: 6; W44: 6; W52: 6
PFG-F1-HOE-FUR-MEL-FUE |  |  | FL1MECH | [5 empty] | Service on heat exchanger 2 |  | 8 W | 1 | 16 | 16 | * | W4: 16; W12: 16; W20: 16; W28: 16; W36: 16; W44: 16; W52: 16
REVERSAL
PFG-F1-HOE-FUR-MEL-REV |  |  | FL1ELEC | F1-HOE-WKS | A | ZJBR | 1 | 489 | Brake changes on Z&J valves |  | 13 W | 2 | 4 | 2 |  | W12: 4; W25: 4; W38: 4; W51: 4
PFG-F1-HOE-FUR-MEL-REV |  |  | FL1ELEC | F1-HOE-WKS | A | ZJSE | 2 | 5404 | Service on Z & J valves Electrical |  | 4 W | 2 | 4 | 2 |  | W4: 4; W8: 4; W12: 4; W16: 4; W20: 4; W24: 4; W28: 4; W32: 4; W36: 4; W40: 4; W44: 4; W48: 4; W52: 4
PFG-F1-HOE-FUR-MEL-REV |  |  | FL1MECH | F1-HOE-WKS | A | AIRM | 1 | 381 | Air motor service on Z & J airmotors |  | 4 W | 1 | 4 | 4 |  | W4: 4; W8: 4; W12: 4; W16: 4; W20: 4; W24: 4; W28: 4; W32: 4; W36: 4; W40: 4; W44: 4; W48: 4; W52: 4
PFG-F1-HOE-FUR-MEL-REV |  |  | FL1MECH | F1-HOE-WKS | A | ZJSE | 1 | 490 | Service on Z & J valves Mechanical |  | 4 W | 1 | 4 | 4 |  | W4: 4; W8: 4; W12: 4; W16: 4; W20: 4; W24: 4; W28: 4; W32: 4; W36: 4; W40: 4; W44: 4; W48: 4; W52: 4
STRUCTURE (SP3 FURNACE)
PFG-F1-HOE-FUR-MEL-STR | 10000807 | FRONT WALL | FL1MECH | F1-HOE-WKS | E | 17 | 1 | 412 | Daily insp.on front wall confirm weekly |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
PFG-F1-HOE-FUR-MEL-STR |  |  | FL1MECH | F1-HOE-WKS | A | F1SC | 1 | 467 | Inspection on superstructure & crown |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
PFG-F1-HOE-FUR-MEL-STR | 10000805 | SIDE AND BOTTOM BLOCKS | FL1MECH | F1-HOE-WKS | A | BLIN | 1 | 493 | Block inspection melt end |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
REGEN
PFG-F1-HOE-FUR-REG | 10000850 | REFRACTORY (REGEN) | FL1MECH | F1-HOE-REGEN | A | 208 | 1 | 5382 | FLOAT HOT END REGEN BASE LHS INSPECTION |  | 12 W | 2 | 2 | 1 |  | W8: 2; W20: 2; W32: 2; W44: 2
PFG-F1-HOE-FUR-REG | 10000850 | REFRACTORY (REGEN) | FL1MECH | F1-HOE-REGEN | A | 208 | 1 | 5383 | FLOAT HOT END REGEN BASE RHS INSPECTION |  | 12 W | 2 | 2 | 1 |  | W8: 2; W20: 2; W32: 2; W44: 2
PFG-F1-HOE-FUR-REG |  |  | FL1MECH | F1-HOE-WKS | T | 8 | 1 | 465 | Daily inspection on regens conf. weekly |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
WAIST
PFG-F1-HOE-FUR-WAI |  |  | FL1MECH | F1-HOE-WKS | A | STSE | 1 | 473 | Service on stirrers |  | 2 W | 1 | 1 | 1 | bar: W2; W4; W6; W8; W10; W12; W14; W16; W18; W20; W22; W24; W26; W28; W30; W32; W34; W36; W38; W40; W42; W44; W46; W48; W50; W52
PFG-F1-HOE-FUR-WAI |  |  | FL1MECH | F1-HOE-WKS | A | STIRPLUM | 1 | 485 | Service on waist (stirrers) by plumber |  | 2 W | 1 | 1 | 1 | bar: W2; W4; W6; W8; W10; W12; W14; W16; W18; W20; W22; W24; W26; W28; W30; W32; W34; W36; W38; W40; W42; W44; W46; W48; W50; W52
WORK END
PFG-F1-HOE-FUR-WOR | 10000877 | WORKING END FANS AND DUCTING | FL1ELEC | F1-HOE-WKS | A | FANS | 2 | 2403 | Working End fans filters MF |  | 1W/2D | 1 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PFG-F1-HOE-FUR-WOR | 10000876 | PORTABLE BURNERS | FL1ELEC | F1-HOE-WKS | E | 24 | 1 | 454 | Service on portable burners |  | 8 W | 1 | 1 | 1 | bar: W8; W16; W24; W32; W40; W48
PFG-F1-HOE-FUR-WOR | 10000881 | SIDE AND BOTTOM BLOCKS | FL1MECH | F1-HOE-WKS | A | BLIN | 1 | 386 | Block inspection work end |  | 1W/5D | 1 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
LEHR
PFG-F1-HOE-LEH |  |  | FL1MECH | F1-HOE-WKS | A | LERHPLUM | 1 | 2823 | Inspection - Lehr service mains(Plumber) |  | 1W/5D | 1 | 2.5 | 2.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
DRIVE MECHANISM
PFG-F1-HOE-LEH-DRI | 10000926 | LEHR DRIVE | FL1ELEC | F1-HOE-WKS | E | 30 | 3 | 445 | Lehr main & standby drive on lehr |  | 7 W | 1 | 3 | 3 |  | W4: 3; W11: 3; W18: 3; W25: 3; W32: 3; W39: 3; W46: 3
PFG-F1-HOE-LEH-DRI | 10000926 | LEHR DRIVE | FL1MECH | F1-HOE-WKS | E | 30 | 2 | 444 | Lehr drive on lehr |  | 1 W | 1 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HEATING AND COOLING
PFG-F1-HOE-LEH-HEA |  |  | FL1ELEC | F1-HOE-WKS | A | LFAN | 2 | 2621 | Service Lehr fans & control |  | 12 W | 1 | 8 | 8 |  | W3: 8; W15: 8; W27: 8; W39: 8; W51: 8
PFG-F1-HOE-LEH-HEA |  |  | FL1MECH | F1-HOE-WKS | A | LFAN | 1 | 447 | Service on lehr fans |  | 1 W | 1 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
MASS AIR COOLING
PFG-F1-HOE-LEH-HEA-MAS |  |  | FL1ELEC | F1-HOE-WKS | A | FMCO | 1 | 411 | Fan motors&controls on mass air cooling |  | 8 W | 1 | 1.5 | 1.5 |  | W8: 1.5; W16: 1.5; W24: 1.5; W32: 1.5; W40: 1.5; W48: 1.5
PYRO COOLING DELETE
PFG-F1-HOE-LEH-HEA-PYR |  |  | FL1ELEC | F1-HOE-WKS | A | PYRC | 1 | 458 | Service on pyro fans & pumps |  | 13 W | 1 | 1 | 1 | bar: W12; W25; W38; W51
PFG-F1-HOE-LEH-HEA-PYR |  |  | FL1ELEC | F1-HOE-WKS | A | FIPC | 1 | 410 | Filter service on pyro cooling fans |  | 4 W | 1 | 1 | 1 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
[9 empty] | Total | Average | [5 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
[9 empty] | 1190.5 | 22.9 | Control - Man Hrs Required |  |  |  |  | 18 | 9.5 | 13.5 | 31.5 | 10.5 | 9.5 | 13.5 | 36.5 | 10.5 | 13.5 | 10.5 | 83.5 | 16.5 | 13.5 | 10.5 | 99.5 | 28.5 | 9.5 | 13.5 | 31.5 | 29.5 | 13.5 | 13.5 | 33.5 | 21.5 | 9.5 | 13.5 | 31.5 | 10.5 | 9.5 | 13.5 | 34.5 | 10.5 | 13.5 | 10.5 | 43.5 | 16.5 | 33.5 | 10.5 | 40.5 | 10.5 | 74.5 | 13.5 | 31.5 | 13.5 | 13.5 | 29.5 | 31.5 | 16.5 | 9.5 | 18.5 | 31.5
[9 empty] | 958 | 18.4 | Elect - Man Hrs Required |  |  |  |  | 12 | 11 | 24 | 29 | 12 | 11 | 10 | 31.5 | 12 | 12.5 | 13 | 48 | 12 | 11 | 24 | 34 | 12 | 14 | 10 | 22.5 | 12 | 13.5 | 10 | 31.5 | 24.5 | 11 | 24 | 25 | 12 | 11 | 10 | 34.5 | 12 | 12.5 | 10 | 22.5 | 12 | 36.5 | 27 | 35 | 12 | 11 | 10 | 22.5 | 12 | 15.5 | 10 | 31.5 | 12 | 11 | 33.5 | 25
[9 empty] | 4971 | 95.6 | Mech - Man Hrs Required |  |  |  |  | 85 | 89 | 85 | 122 | 85 | 89 | 85 | 126 | 85 | 89 | 85 | 123 | 85 | 89 | 85 | 122 | 85 | 89 | 85 | 126 | 85 | 89 | 85 | 122 | 85 | 89 | 85 | 122 | 85 | 89 | 85 | 126 | 85 | 89 | 85 | 122 | 85 | 90 | 85 | 122 | 85 | 89 | 85 | 126 | 85 | 89 | 85 | 122 | 85 | 89 | 85 | 122